## sample_activities
id | name | wbs_code | predecessors | dist_type | a | m | b | category
1 | Basic & detail engineering | 1.1 |  | betapert | 20 | 30 | 45 | design
2 | Permitting & approvals | 1.2 | 1 | betapert | 15 | 25 | 50 | permitting
3 | Site preparation | 2.1 | 1 | betapert | 5 | 10 | 18 | site_preparation
4 | Civil works & foundations | 2.2 | 3 | betapert | 20 | 30 | 50 | civil_works
5 | Electromechanical assembly | 3.1 | 2,4 | betapert | 25 | 40 | 65 | electromechanical
6 | Piping installation | 3.2 | 4 | betapert | 15 | 22 | 35 | piping
7 | Instrumentation & control | 3.3 | 5,6 | betapert | 10 | 15 | 25 | instrumentation
8 | Testing & verification | 4.1 | 7 | betapert | 8 | 12 | 22 | testing
9 | Commissioning | 4.2 | 8 | betapert | 10 | 18 | 35 | commissioning
10 | Handover & closeout | 4.3 | 9 | betapert | 5 | 7 | 14 | startup