## Activities
ID | WBS Code | Activity Name | Predecessors (comma-separated IDs) | Distribution Type (triangular/betapert) | Optimistic (days) | Most Likely (days) | Pessimistic (days) | Category | Notes
1 | 1.1 | Ingeniería básica y de detalle |  | betapert | 20 | 30 | 45 | design
2 | 1.2 | Gestión de permisos | 1 | betapert | 15 | 25 | 50 | permitting
3 | 2.1 | Preparación del terreno | 1 | betapert | 5 | 10 | 18 | site_preparation
4 | 2.2 | Obra civil y cimentaciones | 3 | betapert | 20 | 30 | 50 | civil_works
5 | 3.1 | Montaje electromecánico | 2,4 | betapert | 25 | 40 | 65 | electromechanical
6 | 3.2 | Instalación de tuberías | 4 | betapert | 15 | 22 | 35 | piping
7 | 3.3 | Instrumentación y control | 5,6 | betapert | 10 | 15 | 25 | instrumentation
8 | 4.1 | Pruebas y verificación | 7 | betapert | 8 | 12 | 22 | testing
9 | 4.2 | Puesta en marcha | 8 | betapert | 10 | 18 | 35 | commissioning
10 | 4.3 | Entrega y cierre | 9 | betapert | 5 | 7 | 14 | startup

## Instructions
ACTIVITY TEMPLATE - INSTRUCTIONS
This template is for entering project activity data for Monte Carlo simulation.
COLUMN DESCRIPTIONS:
- ID: Unique numeric identifier for each activity
- WBS Code: Work Breakdown Structure code (optional)
- Activity Name: Descriptive name of the activity
- Predecessors: Comma-separated IDs of activities that must finish before this one starts
- Distribution Type: 'triangular' or 'betapert' (recommended: betapert)
- Optimistic (days): Best-case duration estimate (a)
- Most Likely (days): Most probable duration estimate (m)
- Pessimistic (days): Worst-case duration estimate (b)
- Category: Activity category for classification and analysis
VALID CATEGORIES:
design, permitting, site_preparation, civil_works, electromechanical,
piping, instrumentation, electrical, testing, commissioning, startup
NOTES:
- Optimistic <= Most Likely <= Pessimistic must always hold
- BetaPERT distribution uses lambda=4 weighting on the most likely value
- Predecessors define Finish-to-Start relationships
- All durations should be in the same time unit (calendar days or working days)