## Risk Registry
Risk ID | Risk Name | Description | Probability (0-1) | Impact Distribution (triangular/betapert/uniform) | Impact Min (days) | Impact Most Likely (days) | Impact Max (days) | Affected Activities (comma-separated IDs or 'all') | Risk Category | Mitigation Available | Status (active/mitigated/closed)
R1 | Unexpected contaminant | Atypical contaminant discovered requiring process redesign | 0.25 | triangular | 8 | 15 | 28 | 1,2,5 | technical | No | active
R2 | Extreme weather event | Severe weather causing construction delays | 0.2 | triangular | 5 | 10 | 20 | 3,4,5,6 | environmental | No | active
R3 | Equipment delivery delay | Late delivery of critical equipment from vendor | 0.3 | betapert | 10 | 20 | 45 | 5,6 | supply_chain | Yes | active
R4 | Regulatory change | New regulatory requirements during construction | 0.15 | triangular | 15 | 30 | 60 | 1,2 | regulatory | No | active
R5 | Unidentified risk reserve | Unknown-unknown risk events | 0.07 | uniform | 15 | 45 | 90 | all | residual | No | active